## Product Backlog
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | Complexity | Risk/ Impact(L-Low, M- Medium, H-High) | Type | Comments
1 | 1 |  | M | Us:101 | User must create his Account | Very Simple | L | Functional
2 | 2 |  | M | Us:102 | User must login into the application | Complex | M | Functional
3 | 3 |  | M | Us:103 | User can apply for learner license | Very Simple | L | Technical
4 | 4 |  | M | Us:104 | User can apply for driving license | Very Simple | L | Technical
5 | 5 |  | M | Us:105 | User should have 12-digit Unique Identification number | Average | L | Technical
6 | 6 |  | M | Us:106 | User can pay the fee and print receipt | Simple | L | Technical
7 | 7 |  | M | Us:107 | User can schedule appointment for learning license test | Very Simple | L | Technical
8 | 8 |  | S | Us:108 | User can view the application status | Very Simple | L | Technical
9 | 9 |  | C | Us:109 | User can cancel or modify the test time | Simple | L | Technical
10 | 10 |  | C | Us: 110 | User can view the result | Very Simple | L | Technical
11 | 11 |  | S | Us: 111 | User can change their credentials (Forgot Password) | Average | L | Technical
12 | 12 |  | M | Us: 112 | Admin can login into the application | Complex | H | Functional
13 | 13 |  | M | Us: 113 | Admin can add Users | Average | L | Technical
14 | 14 |  | S | Us: 114 | Admin can view application | Very Simple | L | Technical
15 | 15 |  | S | Us: 115 | Admin can cancel or modify User application | Very Simple | L | Technical
16 | 16 |  | S | Us: 116 | Admin can schedule test | Simple | L | Technical
17 | 17 |  | C | Us: 117 | Admin can delete the account of User | Very Simple | L | Technical
18 | 18 |  | W | Us: 118 | Third party applications like email & sms integrations. | Very Simple | L | Non-Functional
19 | 19 |  | W | Us: 119 | Payments are not yet accepted by the application | Very Simple | L | Non-Functional
20 | 20 |  | M | Us: 120 | Authentication of the User(Valid/Invalid User) | Average | L | Functional
21 | 21 |  | C | Us: 121 | Session Timeout(if no activity) | Complex | M | Functional
22 | 22 |  | S | Us: 122 | User can Logout | Average | L | Functional
23 | 23 |  | C | Us: 123 | Asking for choice again on wrong selection | Average | L | Technical